## Product backlog
Product Backlog | Priority | Status | Day finished
Hypothesis | 5 | Verify
Aim of the project | 5 | Verify
References to related work | 5 | Verify
Materials and methods | 5 | Verify
ROS tutorials | 4 | Done
Write to Lars-Peter | 5 | Done | 2016-12-29
Mail to Kjeld (invite to drive) | 4 | Done
Acquire Raspberry Pi | 2 | On going
Application possibilities | 4 | Verify
Time schedule/Mile Stone | 3 | Verify
Camera & videofeed through ROS
ROS on PI3 |  | Done | 2017-02-08
ROS on laptop |  | Done | 2017-02-08
Connect camera to PI (data - ROS-Node)
Datastream from PI to laptop (still photo)
Computervision with python/C++ IDE |  | Done | 2017-03-01
Take pictures with colorful objects |  | Done | 2017-03-01
start to manipulate pictures |  | Done | 2017-03-01
Write A* library with any functionalities (work on any picture) |  | Done | 2017-03-01
roadmaps libraries. generelle functions ( work on any pictures) |  | Done | 2017-03-01
git folders with our libraries |  | Done | 2017-03-01
Computervision
ROS node for image capture
Workspace boundaries |  | Done | 2017-03-01
Height from workspace (scalability)
Incorp. in ROS-Node
Recognize robot
Robot control
Robot physical model
Engine control
Engine / robot feedback.
Mapping route ("turtlesim")
"simulating?"
incorp all in ROS-Node.
Online planner with obstacle avoid.
Update pos from camera
Update pos from robot feedback
Estimate pos (Kalman filter?)
Roadmaps (shortest path)
Mount camera on drone & update pos input from drone

## Sprint 1
29/12-16 - 12/1-17
Subject | Priority[1-5] | To do | In Process |  | To verify | Done
|  |  | Thor | Mark | Hypothesis
| 5 |  |  |  | Aim of the project
| 5 |  |  |  | References to related work
| 5 |  |  |  | Materials and methods
5
4
| 5 |  |  |  |  | Write to Lars-Peter
| 4 |  |  |  |  | Mail to Kjeld (invite to drive)
| 2 |  | Acquire Raspberry Pi
| 4 |  |  |  | Application possibilities
| 3 |  |  |  | Time schedule

## Sprint 2
9/2/2017 - 23/2/2017 |  | In process | Done
To do | Priority[1-5]
Computervision with python/C++ IDE | 1 | 2017-02-09 | 2017-03-01
Take pictures with colorfull objects | 3 |  | 2017-03-01
Write A* library with any functionalities (work on any picture) | 3 |  | 2017-03-01
Create map libraries. General functions (create, plot etc) | 2 | 2017-02-09 | 2017-03-01
Git folders with our libraries | 1 | 2017-02-09 | 2017-03-01
ROS on PI3 | 4 | 2017-02-09 | 2017-02-09
ROS on laptop | 4 | 2017-02-09 | 2017-02-09
Sprint ended on 01/03/2017. Was delayed because of vacation and eksams

## Sprint 3
23/2/2017-15/03/2017 |  | In process | Done
To do | Priority[1-5]
Sprint meeting with Kjeld | 1
ROS node with computervision (imgMatrix_v1) +publish | 1 | 01/03-2017 | 06/03-2017
ROS node with pathfinding (aStar) +subscribe | 1 | 01/03-2017 | 02/03-2017
Set up 2 remote ROS nodes and test them | 3
Refine report | 2 | 09/03-2017
Git frobomind & readup | 5
Document CV | 2 | 06/03-2017
Document a* | 2 | 06/03-2017
Research CV | 4
Software diagrams | 3 | 06/03-2017
Latex report template | 3 | 06/03-2017
*Sprint changed due to new information* |  | 12/03-2017
Marker locator / ros node for video capture
Change sending format from txt to matrix | 1
Interface with frobit
Talk to mathias Hoejgaard about mapping

## Sprint 4
16/03/2017-30/03/2017 |  | In process | Done
To do | Priority[1-5]
Install ubuntu & ROS on Frobit | 1
Make Frobit demo work IRL | 4
Modify MarkerCaptureROS: cropping, obstacle recognition | 2
Pathfinding ROS node in CPP | 1
MarkerLocator pattern recognition | 1
A* should output waypoint coordinates instead of all coordinates | 2
MarkerCaptureROS.py on laptop1 displayimage on laptop 2 | 3
MarkerCapture, stream of Images | 5

## Sprint 5
31/03/2017-14/04/2017 |  | In process | Done
To do | Priority[1-5]
Pathfinding ROS node in CPP | 1
MarkerCaptureROS.py on laptop1 displayimage on laptop 2 | 4
Print MarkerLocator Markers | 4
Mount marker on robot | 3
Build new test course | 4
Subscribe on markerlocator | 2
A* should output waypoint coordinates instead of all coordinates | 2
A* coordinates, saved in frobit waypoint mission | 3
A* input should be cv image ptr instead of 2 dimensional vector | 1

## Sprint 6
|  | In process | Done
To do | Priority[1-5]
Publishing coords to Frobit waypoint nav
Motor tics for frobit | 5
wheel axis distance frobit | 5
misc frobit pro setup
Test with cardboard | 1
raspberry pi sleep mode | 4
publish waypoints to frobit | 1
remap from pixels to meters | 1
Height of camera /drone | 3
distance between 2 markerlocators | 2